## Sheet1
PLAN FOR PROJECT MACHINE LEARNING
Task | Week1 | Week2 | Week3 | Week4 | Week5 | Week6 | Week7 | Week8 | Week9 | Week10 | Week11 | Week12 | Week13 | Week14 | Week15
Documents for project and Definition | bar: Week1
Determine purpose of forecast | bar: Week1
Collect Data set | bar: Week2
Choose and Analysis (Data exploration,algorithms) | bar: Week3 to Week4
Analysis Techniques | bar: Week4
Methodology(Data Preprocessing) | bar: Week5 to Week7
Implement | bar: Week7 to Week11
Check forecast accuracy | bar: Week11 to Week15